## Instructions
Eribé Data Migration – Stage 1: Audit & Profile Workbook
Companion workbook to the Stage 1 Audit & Profile Report
How to use this workbook
• Source Inventory | List all source systems, owners, and record volumes.
• Data Dictionary | Map every LOB source field to its BlueCherry target. Flag gaps and transformations.
• Profiling Results | Paste or enter statistical profiling data per entity (nulls, duplicates, ranges).
• Quality Scorecard | Score each entity against the four quality dimensions and assign RAG status.
• Issue Register | Log all data quality issues discovered. Assign severity and owner.
• Risk Register | Document migration risks arising from audit findings.
• Change Log | Track all changes made to this workbook.

## Source Inventory
Target System: BlueCherry ERP – Load Template Reference
BlueCherry Entity / System | Load Template Type | Upload Format | BlueCherry Table Code | Est. Records (from LOB) | BlueCherry Contact | Notes
BlueCherry ERP | BlueCherry (version TBC) | SQL Server | 19 entities – see Data Dictionary | ~TBC (profiling required) | Frances Healy | TARGET system — data will be loaded into BlueCherry from LOB source applications
Color | BlueCherry Load Template | XLS upload | ZZXCOLRR | TBC | Eribé data owner | 6 fields
HS Number | BlueCherry Load Template | XLS upload | ZZXHSNOR | TBC | Eribé data owner | 15 fields
Location | BlueCherry Load Template | XLS upload | ZZXLOCAR | TBC | Eribé data owner | 19 fields
Merchandise Group | BlueCherry Load Template | XLS upload | ZZXPGRPR | TBC | Eribé data owner | 8 fields – includes G/L Code
Salesperson | BlueCherry Load Template | XLS upload | ZZXSLSPR | TBC | Eribé data owner | 12 fields
Size Ranges | BlueCherry Load Template | XLS upload | SIZERANGEDC | TBC | Eribé data owner | 83 fields – up to 50 size slots
Style Master | BlueCherry Load Template | XLS upload | ZZXSTYLR | TBC | Eribé data owner | 130 fields – critical path entity
Stock | BlueCherry Load Template | XLS upload | STOCKADJ | TBC | Eribé data owner | 16 fields – depends on Style/Color/Location
Customer Master | BlueCherry Load Template | XLS upload | ZZXCUSTR | TBC | Eribé data owner | 42 fields — core customer record
Customer Bill To | BlueCherry Load Template | XLS upload | ZZXBILLR | TBC | Eribé data owner | 11 fields — billing addresses
Customer Credit | BlueCherry Load Template | XLS upload | ZZHCUSTR | TBC | Eribé data owner | 30 fields — credit limits & terms
Customer Department | BlueCherry Load Template | XLS upload | ZZXCDEPR | TBC | Eribé data owner | 4 fields — department codes
Customer Contact | BlueCherry Load Template | XLS upload | ZZXCOMMU | TBC | Eribé data owner | 5 fields — contacts & communications
Customer Comment | BlueCherry Load Template | XLS upload | ZZXCCMTR | TBC | Eribé data owner | 3 fields — comment lines
Customer Notes | BlueCherry Load Template | XLS upload | SYSNOTES | TBC | Eribé data owner | 2 fields — long-form notes
Customer Sales | BlueCherry Load Template | XLS upload | ZZXCSLSR | TBC | Eribé data owner | 37 fields — sales terms & salesperson
Customer Price | BlueCherry Load Template | XLS upload | ZZXCSTPR | TBC | Eribé data owner | 8 fields — customer-specific pricing
Customer Ship Thru | BlueCherry Load Template | XLS upload | ZZXDISTR | TBC | Eribé data owner | 13 fields — ship-through addresses
Customer Store | BlueCherry Load Template | XLS upload | ZZXSTORR | TBC | Eribé data owner | 26 fields — store/ship-to addresses per customer

## Data Dictionary
Data Dictionary – LOB Source Fields → BlueCherry Target Mapping
Load Order | BlueCherry Target Entity | Target Field (BlueCherry) | Data Type | Field Spec | Sample / Default | LOB Source Table | LOB Source Field | Transformation / Notes | Target Field (BlueCherry)
Step 1 | Color | ← 6 fields ¦ BlueCherry upload sheet: see Source Inventory
1 | Color | Color | Code | Char(5) |  | [BC Table – TBD] | [TBD] | Primary key – color code | Unmapped
1 | Color | Color Name | Text | Char(30) |  | [BC Table – TBD] | [TBD] |  | Unmapped
1 | Color | Color Setup Group | Code | Char(7) |  | [BC Table – TBD] | [TBD] | Groups colors for style setup | Unmapped
1 | Color | Color NRF Code | Code | Char(3) |  | [BC Table – TBD] | [TBD] | Industry standard NRF color code | Unmapped
1 | Color | Active OK | Option | Char(1) | Y | [BC Table – TBD] | [TBD] | Y/N flag | Unmapped
1 | Color | Color Desc | Text | Char(10) |  | [BC Table – TBD] | [TBD] | Short description | Unmapped
Step 2 | Size Ranges | ← 12 fields ¦ BlueCherry upload sheet: see Source Inventory
2 | Size Ranges | Division | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
2 | Size Ranges | Size Code | Code | Char(3) |  | [BC Table – TBD] | [TBD] | Primary key | Unmapped
2 | Size Ranges | Size Code Desc | Text | Char(30) |  | [BC Table – TBD] | [TBD] |  | Unmapped
2 | Size Ranges | Core Size High | Integer | Integer |  | [BC Table – TBD] | [TBD] |  | Unmapped
2 | Size Ranges | Core Size Low | Integer | Integer |  | [BC Table – TBD] | [TBD] |  | Unmapped
2 | Size Ranges | Allow Dimen/Pack | Option | Char(1) | Y | [BC Table – TBD] | [TBD] |  | Unmapped
2 | Size Ranges | Use Dimension As Size | Option | Char(1) |  | [BC Table – TBD] | [TBD] |  | Unmapped
2 | Size Ranges | Active OK | Option | Char(1) | Y | [BC Table – TBD] | [TBD] |  | Unmapped
2 | Size Ranges | Dimen/Pack | Text | Char(50) |  | [BC Table – TBD] | [TBD] | Pack/dimension description | Unmapped
2 | Size Ranges | Size Desc 01–24 | Text | Char(10) |  | [BC Table – TBD] | [TBD] | 24 individual size label fields | Review
2 | Size Ranges | Size 1–24 | Code | Char(5) |  | [BC Table – TBD] | [TBD] | 24 individual size value fields | Review
2 | Size Ranges | Size Desc 25–50 | Text | Char(10) |  | [BC Table – TBD] | [TBD] | Extended sizes – 26 additional descriptors | Review
Step 3 | Merchandise Group | ← 8 fields ¦ BlueCherry upload sheet: see Source Inventory
3 | Merchandise Group | Division | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
3 | Merchandise Group | Merchandise Group Code | Code | Char(9) |  | [BC Table – TBD] | [TBD] | Primary key | Unmapped
3 | Merchandise Group | Group Name | Text | Char(30) |  | [BC Table – TBD] | [TBD] |  | Unmapped
3 | Merchandise Group | Merchandise Group Type | Option | Char(1) |  | [BC Table – TBD] | [TBD] | Get valid values from BC | Review
3 | Merchandise Group | Active OK | Option | Char(1) | y | [BC Table – TBD] | [TBD] | Y/N flag | Unmapped
3 | Merchandise Group | Inactive in VS | Option | Char(1) |  | [BC Table – TBD] | [TBD] |  | Unmapped
3 | Merchandise Group | NMFC Code | Code | Char(8) |  | [BC Table – TBD] | [TBD] | Freight classification code | Unmapped
3 | Merchandise Group | G/L Code | Code | Char(15) |  | [BC Table – TBD] | [TBD] | Links to finance – validate | Review
Step 4 | HS Number | ← 15 fields ¦ BlueCherry upload sheet: see Source Inventory
4 | HS Number | Description | Text | Char(80) |  | [BC Table – TBD] | [TBD] | HS description | Unmapped
4 | HS Number | HS Id | Code | Char(32) |  | [BC Table – TBD] | [TBD] | Primary key | Unmapped
4 | HS Number | Unit Of Measure | Code | Char(4) |  | [BC Table – TBD] | [TBD] |  | Unmapped
4 | HS Number | Notes | Text | Unlimited |  | [BC Table – TBD] | [TBD] | Free text notes | Unmapped
4 | HS Number | Country | Code | Char(3) |  | [BC Table – TBD] | [TBD] | From country | Unmapped
4 | HS Number | To Country | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
4 | HS Number | To HS Number | Code | Char(12) |  | [BC Table – TBD] | [TBD] |  | Unmapped
4 | HS Number | Duty Percent | Decimal | Num(6,2) |  | [BC Table – TBD] | [TBD] |  | Unmapped
4 | HS Number | Duty Rate | Decimal | Num(6,2) |  | [BC Table – TBD] | [TBD] |  | Unmapped
4 | HS Number | Duty Weight | Decimal | Num(6,2) |  | [BC Table – TBD] | [TBD] |  | Unmapped
4 | HS Number | Quota Category | Code | Char(14) |  | [BC Table – TBD] | [TBD] |  | Unmapped
4 | HS Number | To International Region | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
4 | HS Number | Fixed Dollar | Decimal | Num(17,2) |  | [BC Table – TBD] | [TBD] |  | Unmapped
4 | HS Number | RM HS Number | Code | Char(12) |  | [BC Table – TBD] | [TBD] | Raw material HS number | Unmapped
4 | HS Number | Style | Code | Char(50) |  | [BC Table – TBD] | [TBD] | Linked style | Unmapped
Step 5 | Location | ← 19 fields ¦ BlueCherry upload sheet: see Source Inventory
5 | Location | Location | Code | Char(6) |  | [BC Table – TBD] | [TBD] | Primary key | Unmapped
5 | Location | Location Name | Text | Char(60) |  | [BC Table – TBD] | [TBD] |  | Unmapped
5 | Location | RM Location | Code | Char(6) |  | [BC Table – TBD] | [TBD] | Raw material location | Unmapped
5 | Location | Currency | Code | Char(3) |  | [BC Table – TBD] | [TBD] | Currency code e.g. GBP | Unmapped
5 | Location | Loc Type | Option | Char(1) |  | [BC Table – TBD] | [TBD] | Location type code – get valid values | Review
5 | Location | Warehouse Type | Option | Char(1) |  | [BC Table – TBD] | [TBD] | Warehouse type code – get valid values | Review
5 | Location | Terms | Code | Char(3) |  | [BC Table – TBD] | [TBD] | Payment terms code | Unmapped
5 | Location | Ship Terms | Code | Char(3) |  | [BC Table – TBD] | [TBD] | Shipping terms code | Unmapped
5 | Location | Address1 | Text | Char(60) |  | [BC Table – TBD] | [TBD] |  | Unmapped
5 | Location | Address2 | Text | Char(60) |  | [BC Table – TBD] | [TBD] |  | Unmapped
5 | Location | City | Text | Char(25) |  | [BC Table – TBD] | [TBD] |  | Unmapped
5 | Location | State | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
5 | Location | Zip Code | Code | Char(10) |  | [BC Table – TBD] | [TBD] |  | Unmapped
5 | Location | Country | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
5 | Location | Active OK | Option | Char(1) | Y | [BC Table – TBD] | [TBD] | Y/N flag | Unmapped
5 | Location | Shippable | Option | Char(1) | Y | [BC Table – TBD] | [TBD] | Y/N flag | Unmapped
5 | Location | Agent | Code | Char(5) |  | [BC Table – TBD] | [TBD] |  | Unmapped
5 | Location | Organisation Code | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
5 | Location | AP Vendor | Code | Char(20) |  | [BC Table – TBD] | [TBD] | Accounts payable vendor link | Unmapped
Step 6 | Salesperson | ← 12 fields ¦ BlueCherry upload sheet: see Source Inventory
6 | Salesperson | Salesperson | Code | Char(6) |  | [BC Table – TBD] | [TBD] | Primary key | Unmapped
6 | Salesperson | Salesperson Name | Text | Char(30) |  | [BC Table – TBD] | [TBD] |  | Unmapped
6 | Salesperson | Address1 | Text | Char(60) |  | [BC Table – TBD] | [TBD] |  | Unmapped
6 | Salesperson | Address2 | Text | Char(60) |  | [BC Table – TBD] | [TBD] |  | Unmapped
6 | Salesperson | City | Text | Char(25) |  | [BC Table – TBD] | [TBD] |  | Unmapped
6 | Salesperson | State | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
6 | Salesperson | Zip Code | Code | Char(10) |  | [BC Table – TBD] | [TBD] |  | Unmapped
6 | Salesperson | Country | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
6 | Salesperson | Commission | Code | Char(3) |  | [BC Table – TBD] | [TBD] | Commission code | Unmapped
6 | Salesperson | Type | Option | Char(1) |  | [BC Table – TBD] | [TBD] | Salesperson type code – get valid values | Review
6 | Salesperson | Territory | Code | Char(3) |  | [BC Table – TBD] | [TBD] | Territory code | Unmapped
6 | Salesperson | Quota Category | Integer | Integer |  | [BC Table – TBD] | [TBD] |  | Unmapped
Step 7 | Style Master | ← 116 fields ¦ BlueCherry upload sheet: see Source Inventory
7 | Style Master | Division | Code | Char(3) |  | [BC Table – TBD] | [TBD] | Division code | Unmapped
7 | Style Master | Style | Code | Char(12) |  | [BC Table – TBD] | [TBD] | Primary key – style number | Unmapped
7 | Style Master | Color Code | Code | Char(5) |  | [BC Table – TBD] | [TBD] | Must exist in Color | Review
7 | Style Master | Label | Text | Char(50) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Dimen/Pack | Text | Char(50) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Season | Code | Char(5) |  | [BC Table – TBD] | [TBD] | Season code | Unmapped
7 | Style Master | Style Name | Text | Char(60) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Style Description | Text | Text |  | [BC Table – TBD] | [TBD] | Long description | Unmapped
7 | Style Master | Style Type | Option | Char(6) | FG or RM | [BC Table – TBD] | [TBD] | FG = Finished Goods, RM = Raw Material | Review
7 | Style Master | Process Type | Code | Char(5) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Customer Type | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Merch Group A | Code | Char(9) |  | [BC Table – TBD] | [TBD] | Up to 13 merch group slots (A–M) | Review
7 | Style Master | Merch Group B | Code | Char(9) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Merch Group C | Code | Char(9) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Merch Group D | Code | Char(9) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Merch Group E | Code | Char(9) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Merch Group F | Code | Char(9) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Merch Group G–M | Code | Char(9) |  | [BC Table – TBD] | [TBD] | 7 further optional groups | Unmapped
7 | Style Master | size_code | Code | Char(3) |  | [BC Table – TBD] | [TBD] | Must exist in Size Ranges | Review
7 | Style Master | Size Explosion Code | Code | Char(6) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Sizes | Text | Char(50) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Standard Cost | Decimal | Num(14,5) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Retail Price | Decimal | Num(9,2) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Inventory Cost | Decimal | Num(17,8) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | A Level Price | Decimal | Num(14,5) |  | [BC Table – TBD] | [TBD] | Price level A | Unmapped
7 | Style Master | B Level Price | Decimal | Num(14,5) |  | [BC Table – TBD] | [TBD] | Price level B | Unmapped
7 | Style Master | C Level Price | Decimal | Num(14,5) |  | [BC Table – TBD] | [TBD] | Price level C | Unmapped
7 | Style Master | D Level Price | Decimal | Num(14,5) |  | [BC Table – TBD] | [TBD] | Price level D | Unmapped
7 | Style Master | E Level Price | Decimal | Num(14,5) |  | [BC Table – TBD] | [TBD] | Price level E | Unmapped
7 | Style Master | Minimum Multiple | Integer | Integer |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Pack Quantity | Integer | Integer |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Pack Weight | Decimal | Num(7,3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Carton Quantity | Decimal | Num(8,2) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Carton Weight | Decimal | Num(7,3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Style Weight | Decimal | Num(7,3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Style Volume | Decimal | Num(8,5) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Unit Of Measure | Code | Char(4) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Prepack Flag | Option | Char(1) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Length | Decimal | Num(8,3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Length UOM | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Width UOM | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Height UOM | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Weight UOM | Code | Char(4) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Cubic UOM | Code | Char(4) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | WIDTH Form Pkg Builder | Decimal | Num(8,3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | HEIGHT Form Pkg Builder | Decimal | Num(8,3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Carton Length Inches | Decimal | Num(8,3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Carton Width Inches | Decimal | Num(8,3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Carton Height Inches | Decimal | Num(8,3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Total Carton Volume | Decimal | Num(10,3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Carton UOM | Code | Char(4) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | HS Number2 | Code | Char(12) |  | [BC Table – TBD] | [TBD] | Primary HS number | Review
7 | Style Master | HS Id | Code | Char(32) |  | [BC Table – TBD] | [TBD] | Links to HS Number entity | Review
7 | Style Master | European HS Number | Code | Char(12) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Canadian HS Number | Code | Char(12) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Quota Category | Code | Char(14) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | ORIGCNTY | Code | Char(3) |  | [BC Table – TBD] | [TBD] | Country of origin | Unmapped
7 | Style Master | TARGETCNTY | Code | Char(3) |  | [BC Table – TBD] | [TBD] | Target country | Unmapped
7 | Style Master | Country | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Waste Factor | Decimal | Num(7,5) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Active OK | Option | Char(1) | Y | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Style Available | Option | Char(1) | Y | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Color Available | Option | Char(1) | Y | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Shippable | Option | Char(1) | Y | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Orderable | Option | Char(1) | Y | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Invoiceable | Option | Char(1) | Y | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Recyclable | Option | Char(1) | Y | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Discontinued Flag | Option | Char(1) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Return Pkg | Option | Char(1) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Base | Option | Char(1) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Variable | Option | Char(1) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Consumable | Option | Char(1) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Green DOT | Option | Char(1) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Use Serial No. | Option | Char(1) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Shipping Attribute | Option | Char(1) | W | [BC Table – TBD] | [TBD] | Default W | Unmapped
7 | Style Master | Auto assign UPC? | Option | Char(1) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | UPC/EAN Catalog Group Code | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Catalog Destination 1 | Code | Char(10) |  | [BC Table – TBD] | [TBD] | Up to 6 catalog destinations | Unmapped
7 | Style Master | Catalog Destination 2–6 | Code | Char(10) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Primary Vendor | Code | Char(6) |  | [BC Table – TBD] | [TBD] | Primary vendor code | Review
7 | Style Master | Contractor | Code | Char(20) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Leadtime Code | Code | Char(5) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Delivery Code | Code | Char(7) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Cost Template | Code | Char(20) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Third Party Item | Text | Char(50) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Bin/Lot | Text | Char(30) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Expiration Date | Date | Date |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Royalty Class | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Royalty | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Royalty Material | Code | Char(10) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | ROYALTY RIGHT CODE | Code | Char(10) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Royalty Group Code | Code | Char(20) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Style Content Code | Code | Char(6) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Color Setup group | Code | Char(6) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Color NRF Code | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Stitch Count | Decimal | Num(8,0) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | No Of Placements | Decimal | Num(6,0) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Color Count | Decimal | Num(6,0) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Concept Code | Code | Char(5) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Core Art# | Code | Char(50) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Art Height | Decimal | Num(7,3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Art Width | Decimal | Num(7,3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Design No. | Code | Char(50) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Embroidery Code | Code | Char(10) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Material Code | Code | Char(6) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | Style Header UDF 2 | Text | Char(20) |  | [BC Table – TBD] | [TBD] | User defined field | Unmapped
7 | Style Master | Style Hdr UDF 4 | Decimal | Num(9,2) |  | [BC Table – TBD] | [TBD] | User defined field | Unmapped
7 | Style Master | Style Dtl UDF #2 | Text | Char(20) |  | [BC Table – TBD] | [TBD] | User defined field | Unmapped
7 | Style Master | Style Dtl UDF #3 | Text | Char(50) |  | [BC Table – TBD] | [TBD] | User defined field | Unmapped
7 | Style Master | Style UDF Dtl 1 N | Decimal | Num(14,5) |  | [BC Table – TBD] | [TBD] | User defined numeric field | Unmapped
7 | Style Master | UDF Date 1 | Date | Date |  | [BC Table – TBD] | [TBD] | User defined date field | Unmapped
7 | Style Master | UDF Date 2 | Date | Date |  | [BC Table – TBD] | [TBD] | User defined date field | Unmapped
7 | Style Master | Permit Number | Text | Char(70) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | UDEX | Code | Char(12) |  | [BC Table – TBD] | [TBD] |  | Unmapped
7 | Style Master | GPC | Code | Char(8) |  | [BC Table – TBD] | [TBD] | Global Product Classification | Unmapped
7 | Style Master | Tax Category | Code | Char(25) |  | [BC Table – TBD] | [TBD] |  | Review
Step 8 | Stock | ← 16 fields ¦ BlueCherry upload sheet: see Source Inventory
8 | Stock | Division | Code | Char(3) |  | [BC Table – TBD] | [TBD] |  | Unmapped
8 | Stock | Style | Code | Char(12) |  | [BC Table – TBD] | [TBD] | Must exist in Style Master – load last | Review
8 | Stock | Color Code | Code | Char(5) |  | [BC Table – TBD] | [TBD] | Must exist in Color | Review
8 | Stock | Label | Text | Char(50) |  | [BC Table – TBD] | [TBD] |  | Unmapped
8 | Stock | Dimen/Pack | Text | Char(50) |  | [BC Table – TBD] | [TBD] |  | Unmapped
8 | Stock | Size Bucket | Integer | Integer |  | [BC Table – TBD] | [TBD] |  | Unmapped
8 | Stock | Qty per UPC and PO | Decimal | Num(14,5) |  | [BC Table – TBD] | [TBD] |  | Unmapped
8 | Stock | Adjustment Reason | Code | Char(3) |  | [BC Table – TBD] | [TBD] | Get valid reason codes from BlueCherry | Review
8 | Stock | Quantity Adjustment | Option | Char(1) |  | [BC Table – TBD] | [TBD] | A = Add inventory ¦ S = Negative adjustment | Review
8 | Stock | Location | Code | Char(6) |  | [BC Table – TBD] | [TBD] | Must exist in Location | Review
8 | Stock | Reference Number | Text | Char(50) |  | [BC Table – TBD] | [TBD] |  | Unmapped
8 | Stock | UPC Number | Code | Char(12) |  | [BC Table – TBD] | [TBD] |  | Unmapped
8 | Stock | Bin/Lot | Text | Char(30) |  | [BC Table – TBD] | [TBD] |  | Unmapped
8 | Stock | To Location | Code | Char(6) |  | [BC Table – TBD] | [TBD] | Target location for transfers | Unmapped
8 | Stock | Warehouse Receipt Date | Date | Date |  | [BC Table – TBD] | [TBD] |  | Unmapped
8 | Stock | Cost | Decimal | Num(9,2) |  | [BC Table – TBD] | [TBD] |  | Unmapped
Step 9 ► CUSTOMER MASTER (Table: ZZXCUSTR) — 42 fields ¦ Core customer record — parent of all other customer sub-entities
9 | Customer Master | Customer | Code | Char(7) |  | [LOB: TBD] | [TBD] | Primary key — unique customer ID | Required
9 | Customer Master | Customer Name | Text | Char(40) |  | [LOB: TBD] | [TBD] |  | Required
9 | Customer Master | Customer Parent | Code | Char(7) |  | [LOB: TBD] | TBD | Parent customer for hierarchy grouping | Optional
9 | Customer Master | Doing Business As | Text | Char(40) |  | [LOB: TBD] | TBD | Trading name if different from legal name | Optional
9 | Customer Master | Address1 | Text | Char(60) |  | [LOB: TBD] | [TBD] |  | Required
9 | Customer Master | Address2 | Text | Char(60) |  | [LOB: TBD] | [TBD] |  | Optional
9 | Customer Master | City | Text | Char(25) |  | [LOB: TBD] | [TBD] |  | Required
9 | Customer Master | STATE | Code | Char(3) |  | [LOB: TBD] | [TBD] |  | Required
9 | Customer Master | Zip Code | Text | Char(10) |  | [LOB: TBD] | [TBD] |  | Required
9 | Customer Master | Country | Code | Char(3) |  | [LOB: TBD] | [TBD] | ISO 3-char country code | Required
9 | Customer Master | Old Customer | Code | Char(10) |  | [LOB: TBD] | TBD | Legacy customer reference — clarify usage | Amber
9 | Customer Master | Customer Type | Code | Char(3) |  | [LOB: TBD] | TBD | Coded value — code list required | Amber
9 | Customer Master | Location | Code | Char(6) |  | [LOB: TBD] | [TBD] | FK → Location master | Required
9 | Customer Master | Call Days For Allocation | Integer | Integer |  | [LOB: TBD] | TBD | Planning parameter | Optional
9 | Customer Master | Lead Time for Shipping | Integer | Integer |  | [LOB: TBD] | [TBD] |  | Optional
9 | Customer Master | Use PO Numbers | Flag | Char(1) |  | [LOB: TBD] | TBD | Y/N flag — clarify BC equivalent | Amber
9 | Customer Master | Use Departments | Flag | Char(1) |  | [LOB: TBD] | TBD | Y/N flag — drives Department sub-entity use | Amber
9 | Customer Master | NO DESCRIPTION AVAILABLE | Flag | Char(1) |  | [LOB: TBD] | TBD | Unknown field — needs clarification | Amber
9 | Customer Master | Sku Upc | Flag | Char(1) |  | [LOB: TBD] | TBD | Controls UPC usage on orders | Amber
9 | Customer Master | Customer UDF #1 | Text | Char(20) |  | [LOB: TBD] | TBD | User-defined field — confirm usage | Optional
9 | Customer Master | Customer UDF #2 | Text | Char(21) |  | [LOB: TBD] | TBD | User-defined field — confirm usage | Optional
9 | Customer Master | Active OK | Flag | Char(1) |  | [LOB: TBD] | [TBD] | Active/inactive status | Required
9 | Customer Master | Organization Code | Code | Char(3) |  | [LOB: TBD] | TBD | Coded value — clarify code list | Amber
9 | Customer Master | Calculate Freight | Flag | Char(1) |  | [LOB: TBD] | TBD | Freight calculation flag | Amber
9 | Customer Master | Exclude Freight | Flag | Char(1) |  | [LOB: TBD] | TBD | Exclude from freight calc | Amber
9 | Customer Master | Allow Back Order | Flag | Char(1) |  | [LOB: TBD] | TBD |  | Amber
9 | Customer Master | Tax Exempt | Flag | Char(1) |  | [LOB: TBD] | TBD |  | Amber
9 | Customer Master | Warn on Zero Price | Flag | Char(1) |  | [LOB: TBD] | TBD |  | Optional
9 | Customer Master | Invoice Form | Code | Char(10) |  | [LOB: TBD] | TBD | Invoice layout code | Amber
9 | Customer Master | SPS Billing Code | Code | Char(3) |  | [LOB: TBD] | TBD | EDI billing code | Optional
9 | Customer Master | Pick Ticket Copies | Integer | Integer |  | [LOB: TBD] | TBD |  | Optional
9 | Customer Master | Insurance | Flag | Char(1) |  | [LOB: TBD] | TBD |  | Amber
9 | Customer Master | Allow Duplicate SKU | Flag | Char(1) |  | [LOB: TBD] | TBD |  | Amber
9 | Customer Master | Code | Code | Char(3) |  | [LOB: TBD] | TBD | Division/class code — clarify purpose | Amber
9 | Customer Master | Address 3 | Text | Char(60) |  | [LOB: TBD] | TBD |  | Optional
9 | Customer Master | Address 4 | Text | Char(60) |  | [LOB: TBD] | TBD |  | Optional
9 | Customer Master | Factor Client Number | Code | Char(10) |  | [LOB: TBD] | TBD | Factoring client reference | Optional
9 | Customer Master | Channel | Code | Char(10) |  | [LOB: TBD] | TBD | Sales channel — clarify code list | Amber
9 | Customer Master | BOL Label | Code | Char(8) |  | [LOB: TBD] | TBD | Bill of lading label format | Optional
9 | Customer Master | MBOL_LABEL | Code | Char(8) |  | [LOB: TBD] | TBD | Master BOL label format | Optional
9 | Customer Master | Partner Code | Code | Char(12) |  | [LOB: TBD] | TBD | EDI partner code | Optional
9 | Customer Master | Print Invoice | Flag | Char(1) |  | [LOB: TBD] | TBD | Auto-print invoice flag | Amber
Step 10 ► CUSTOMER BILL TO (Table: ZZXBILLR) — 11 fields ¦ Billing address records for a customer — multiple bill-to codes per customer
10 | Customer Bill To | Customer | Code | Char(7) |  | [LOB: TBD] | [TBD] | FK → Customer Master | Required
10 | Customer Bill To | Bill To Code | Code | Char(7) |  | [LOB: TBD] | [TBD] | Unique bill-to identifier per customer | Required
10 | Customer Bill To | Bill To Name | Text | Char(40) |  | [LOB: TBD] | [TBD] |  | Required
10 | Customer Bill To | Address1 | Text | Char(60) |  | [LOB: TBD] | [TBD] |  | Required
10 | Customer Bill To | Address2 | Text | Char(60) |  | [LOB: TBD] | [TBD] |  | Optional
10 | Customer Bill To | City | Text | Char(25) |  | [LOB: TBD] | [TBD] |  | Required
10 | Customer Bill To | STATE | Code | Char(3) |  | [LOB: TBD] | [TBD] |  | Required
10 | Customer Bill To | Zip Code | Text | Char(10) |  | [LOB: TBD] | [TBD] |  | Required
10 | Customer Bill To | Country | Code | Char(3) |  | [LOB: TBD] | [TBD] | ISO 3-char | Required
10 | Customer Bill To | Active OK | Flag | Char(1) |  | [LOB: TBD] | [TBD] | Default Y | Required
10 | Customer Bill To | Address 3 | Text | Char(60) |  | [LOB: TBD] | TBD |  | Optional
Step 11 ► CUSTOMER CREDIT (Table: ZZHCUSTR) — 30 fields ¦ Credit terms and limits per customer per division — financial controls
11 | Customer Credit | Division | Code | Char(3) |  | [LOB: TBD] | TBD | FK → Division | Required
11 | Customer Credit | Customer | Code | Char(7) |  | [LOB: TBD] | [TBD] | FK → Customer Master | Required
11 | Customer Credit | Assign Date | Date | Date |  | [LOB: TBD] | TBD |  | Optional
11 | Customer Credit | Bypass Checking | Flag | Char(1) |  | [LOB: TBD] | TBD | Bypass credit check flag | Amber
11 | Customer Credit | Entry Date | Date | Date |  | [LOB: TBD] | TBD |  | Optional
11 | Customer Credit | Base Credit Limit | Decimal | Num(15,2) |  | [LOB: TBD] | [TBD] | Credit limit amount | Required
11 | Customer Credit | Credit Expiration Date | Date | Date |  | [LOB: TBD] | TBD |  | Optional
11 | Customer Credit | Term Days Limit | Integer | Integer |  | [LOB: TBD] | TBD | Payment terms days | Optional
11 | Customer Credit | % Limit Up | Decimal | Num(7,2) |  | [LOB: TBD] | TBD | Upper tolerance % on credit limit | Optional
11 | Customer Credit | % Limit Down | Decimal | Num(7,2) |  | [LOB: TBD] | TBD | Lower tolerance % on credit limit | Optional
11 | Customer Credit | Past Due Period | Integer | Integer |  | [LOB: TBD] | TBD |  | Optional
11 | Customer Credit | Past Due Amount | Decimal | Num(15,2) |  | [LOB: TBD] | TBD |  | Optional
11 | Customer Credit | Past Due % | Decimal | Num(7,2) |  | [LOB: TBD] | TBD |  | Optional
11 | Customer Credit | D and B Number | Code | Char(9) |  | [LOB: TBD] | TBD | Dun & Bradstreet number | Optional
11 | Customer Credit | D&B Rating | Code | Char(10) |  | [LOB: TBD] | TBD | D&B credit rating | Optional
11 | Customer Credit | D&B Rating Date | Date | Date |  | [LOB: TBD] | TBD |  | Optional
11 | Customer Credit | Credit Rep. | Code | Char(15) |  | [LOB: TBD] | TBD | Credit representative | Optional
11 | Customer Credit | Collector | Code | Char(15) |  | [LOB: TBD] | TBD |  | Optional
11 | Customer Credit | Credit | Code | Char(1) |  | [LOB: TBD] | TBD | Credit status code — clarify values | Amber
11 | Customer Credit | Credit Hold Reason | Code | Char(3) |  | [LOB: TBD] | TBD | Hold reason code list required | Amber
11 | Customer Credit | Use Factor | Flag | Char(1) |  | [LOB: TBD] | TBD | Factoring enabled flag | Optional
11 | Customer Credit | Factor Code | Code | Char(5) |  | [LOB: TBD] | TBD |  | Optional
11 | Customer Credit | Automatic Factor Approval | Flag | Char(1) |  | [LOB: TBD] | TBD |  | Amber
11 | Customer Credit | Client No. | Code | Char(6) |  | [LOB: TBD] | TBD | Factor client number | Optional
11 | Customer Credit | Finance Charge | Flag | Char(1) |  | [LOB: TBD] | TBD | Apply finance charges flag | Amber
11 | Customer Credit | Dunning Notices Flag | Flag | Char(1) |  | [LOB: TBD] | TBD | Send dunning notices flag | Amber
11 | Customer Credit | Ext Open AR Amt | Decimal | Num(20,7) |  | [LOB: TBD] | TBD | External AR balance — likely historical | Optional
11 | Customer Credit | Ext Past Due Amt | Decimal | Num(20,7) |  | [LOB: TBD] | TBD | External past due balance | Optional
11 | Customer Credit | Ext Avg Days Late | Integer | Integer |  | [LOB: TBD] | TBD | Average days late — historical metric | Optional
11 | Customer Credit | Financial Customer Code | Code | Char(20) |  | [LOB: TBD] | TBD | External finance system reference | Optional
Step 12 ► CUSTOMER DEPARTMENT (Table: ZZXCDEPR) — 4 fields ¦ Customer department codes — used when 'Use Departments' is enabled on Customer Master
12 | Customer Department | Customer | Code | Char(7) |  | [LOB: TBD] | [TBD] | FK → Customer Master | Required
12 | Customer Department | Department | Code | Char(5) |  | [LOB: TBD] | TBD | Department code | Required
12 | Customer Department | Department Name | Text | Char(30) |  | [LOB: TBD] | TBD |  | Required
12 | Customer Department | Division | Code | Char(3) |  | [LOB: TBD] | TBD | FK → Division | Required
Step 13 ► CUSTOMER CONTACT (Table: ZZXCOMMU) — 5 fields ¦ Contact/communication records for a customer (phone, email, fax etc.)
13 | Customer Contact | Customer | Code | Char(7) |  | [LOB: TBD] | [TBD] | FK → Customer Master | Required
13 | Customer Contact | Primary Contact Name | Text | Char(30) |  | [LOB: TBD] | [TBD] |  | Required
13 | Customer Contact | Access Type | Code | Char(20) |  | [LOB: TBD] | TBD | Contact type code (phone/email/fax etc.) | Amber
13 | Customer Contact | Primary Contact Access # | Text | Char(50) |  | [LOB: TBD] | TBD | The actual phone/email/fax value | Required
13 | Customer Contact | Format | Code | Char(15) |  | [LOB: TBD] | TBD | Format code for access number | Amber
Step 14 ► CUSTOMER COMMENT (Table: ZZXCCMTR) — 3 fields ¦ Free-text comment lines attached to a customer record
14 | Customer Comment | Customer | Code | Char(7) |  | [LOB: TBD] | [TBD] | FK → Customer Master | Required
14 | Customer Comment | Line Number | Integer | Integer |  | [LOB: TBD] | TBD | Sequence number for comments | Required
14 | Customer Comment | Comment Code | Code | Char(1) |  | [LOB: TBD] | TBD | Comment type code — clarify values | Amber
Step 15 ► CUSTOMER NOTES (Table: SYSNOTES) — 2 fields ¦ Long-form notes/memo text associated with a customer
15 | Customer Notes | Customer | Code | Char(7) |  | [LOB: TBD] | [TBD] | FK → Customer Master | Required
15 | Customer Notes | Notes | Text | Text |  | [LOB: TBD] | TBD | Free text — long memo | Optional
Step 16 ► CUSTOMER SALES (Table: ZZXCSLSR) — 37 fields ¦ Sales terms and assignment per customer per division — salesperson, terms, pricing
16 | Customer Sales | Customer | Code | Char(7) |  | [LOB: TBD] | [TBD] | FK → Customer Master | Required
16 | Customer Sales | Store | Code | Char(9) |  | [LOB: TBD] | TBD | Store/location code | Optional
16 | Customer Sales | Department | Code | Char(5) |  | [LOB: TBD] | TBD | FK → Customer Department | Optional
16 | Customer Sales | Division | Code | Char(3) |  | [LOB: TBD] | TBD | FK → Division | Required
16 | Customer Sales | Salesperson 1 | Code | Char(6) |  | [LOB: TBD] | [TBD] | FK → Salesperson master | Optional
16 | Customer Sales | Commission 1 | Code | Char(3) |  | [LOB: TBD] | TBD | Commission code for Salesperson 1 | Optional
16 | Customer Sales | Salesperson 2 | Code | Char(6) |  | [LOB: TBD] | TBD | Second salesperson assignment | Optional
16 | Customer Sales | Commission 2 | Code | Char(3) |  | [LOB: TBD] | TBD |  | Optional
16 | Customer Sales | Priority Code | Code | Char(3) |  | [LOB: TBD] | TBD | Order priority code | Amber
16 | Customer Sales | Terms | Code | Char(3) |  | [LOB: TBD] | [TBD] | Payment terms code | Amber
16 | Customer Sales | Use Factor | Flag | Char(1) |  | [LOB: TBD] | TBD |  | Optional
16 | Customer Sales | Factor Code | Code | Char(5) |  | [LOB: TBD] | TBD |  | Optional
16 | Customer Sales | Price Code | Code | Char(1) |  | [LOB: TBD] | TBD | Price code A-E — clarify mapping | Amber
16 | Customer Sales | Supplier Number | Code | Char(15) |  | [LOB: TBD] | TBD | Internal supplier reference | Optional
16 | Customer Sales | Customer Rep. | Code | Char(15) |  | [LOB: TBD] | TBD |  | Optional
16 | Customer Sales | Claims Rep. | Code | Char(15) |  | [LOB: TBD] | TBD |  | Optional
16 | Customer Sales | Credit | Code | Char(1) |  | [LOB: TBD] | TBD | Credit status — default A | Amber
16 | Customer Sales | Credit Hold Reason | Code | Char(3) |  | [LOB: TBD] | TBD |  | Amber
16 | Customer Sales | Automatic Factor Approval | Flag | Char(1) |  | [LOB: TBD] | TBD |  | Amber
16 | Customer Sales | Discount Code | Code | Char(3) |  | [LOB: TBD] | TBD | Discount schedule code | Amber
16 | Customer Sales | Projection | Decimal | Num(9,0) |  | [LOB: TBD] | TBD | Sales projection value | Optional
16 | Customer Sales | Expiration Days | Integer | Integer |  | [LOB: TBD] | TBD | Order expiry days | Optional
16 | Customer Sales | Expiration Basis | Code | Char(1) |  | [LOB: TBD] | TBD | Basis for expiry calc | Optional
16 | Customer Sales | Client No. | Code | Char(10) |  | [LOB: TBD] | TBD | Factor client number | Optional
16 | Customer Sales | Customer Region Code | Code | Char(5) |  | [LOB: TBD] | TBD | Sales region | Optional
16 | Customer Sales | Salesperson 3 | Code | Char(6) |  | [LOB: TBD] | TBD |  | Optional
16 | Customer Sales | Commission 3 | Code | Char(3) |  | [LOB: TBD] | TBD |  | Optional
16 | Customer Sales | Salesperson 4 | Code | Char(6) |  | [LOB: TBD] | TBD |  | Optional
16 | Customer Sales | Commission 4 | Code | Char(3) |  | [LOB: TBD] | TBD |  | Optional
16 | Customer Sales | C/S Hold | Flag | Char(1) |  | [LOB: TBD] | TBD | Customer service hold flag | Amber
16 | Customer Sales | C/S Hold Rsn | Code | Char(3) |  | [LOB: TBD] | TBD | CS hold reason code | Amber
16 | Customer Sales | Price Level Source | Code | Char(1) |  | [LOB: TBD] | TBD | Price level source flag | Amber
16 | Customer Sales | Retail Discount Code | Code | Char(3) |  | [LOB: TBD] | TBD | Retail discount schedule code | Amber
16 | Customer Sales | Division Active | Flag | Char(1) |  | [LOB: TBD] | TBD | Division active status | Required
16 | Customer Sales | Shipping Terms | Code | Char(3) |  | [LOB: TBD] | [TBD] | Shipping terms code | Amber
16 | Customer Sales | Order Type | Code | Char(3) |  | [LOB: TBD] | TBD | Default order type | Amber
16 | Customer Sales | Auto Invoice | Flag | Char(1) |  | [LOB: TBD] | TBD | Auto-invoice on despatch flag | Amber
Step 17 ► CUSTOMER PRICE (Table: ZZXCSTPR) — 8 fields ¦ Customer-specific pricing by style/colour/label — overrides standard price list
17 | Customer Price | Customer | Code | Char(7) |  | [LOB: TBD] | [TBD] | FK → Customer Master | Required
17 | Customer Price | Division | Code | Char(3) |  | [LOB: TBD] | TBD | FK → Division | Required
17 | Customer Price | Style | Code | Char(50) |  | [LOB: TBD] | [TBD] | FK → Style Master | Required
17 | Customer Price | Color | Code | Char(50) |  | [LOB: TBD] | TBD | FK → Color — optional filter | Optional
17 | Customer Price | Label | Code | Char(50) |  | [LOB: TBD] | TBD | Label/brand filter | Optional
17 | Customer Price | Dimen/Pack | Code | Char(50) |  | [LOB: TBD] | TBD | Dimension/pack size filter | Optional
17 | Customer Price | Price | Decimal | Num(14,5) |  | [LOB: TBD] | [TBD] | Customer-specific unit price | Required
17 | Customer Price | Retail Price | Decimal | Num(9,2) |  | [LOB: TBD] | TBD | Suggested retail price | Optional
Step 18 ► CUSTOMER SHIP THRU (Table: ZZXDISTR) — 13 fields ¦ Ship-through/distribution centre addresses for a customer — depends on Bill To
18 | Customer Ship Thru | Customer | Code | Char(7) |  | [LOB: TBD] | [TBD] | FK → Customer Master | Required
18 | Customer Ship Thru | Dist. Center | Code | Char(5) |  | [LOB: TBD] | [TBD] | Distribution centre code | Required
18 | Customer Ship Thru | Ship Thru Name | Text | Char(60) |  | [LOB: TBD] | [TBD] |  | Required
18 | Customer Ship Thru | Address1 | Text | Char(60) |  | [LOB: TBD] | [TBD] |  | Required
18 | Customer Ship Thru | Address2 | Text | Char(60) |  | [LOB: TBD] | [TBD] |  | Optional
18 | Customer Ship Thru | City | Text | Char(25) |  | [LOB: TBD] | [TBD] |  | Required
18 | Customer Ship Thru | STATE | Code | Char(3) |  | [LOB: TBD] | [TBD] |  | Required
18 | Customer Ship Thru | Zip Code | Text | Char(10) |  | [LOB: TBD] | [TBD] |  | Required
18 | Customer Ship Thru | Country | Code | Char(3) |  | [LOB: TBD] | [TBD] | ISO 3-char | Required
18 | Customer Ship Thru | Ship Thru Type | Code | Char(1) |  | [LOB: TBD] | TBD | C=Consolidator, D=Direct — coded | Amber
18 | Customer Ship Thru | Bill To Code | Code | Char(7) |  | [LOB: TBD] | [TBD] | FK → Customer Bill To | Optional
18 | Customer Ship Thru | Active OK | Flag | Char(1) |  | [LOB: TBD] | TBD | Default Y | Required
18 | Customer Ship Thru | EDI Center code | Code | Char(13) |  | [LOB: TBD] | TBD | EDI distribution centre code | Optional
Step 19 ► CUSTOMER STORE (Table: ZZXSTORR) — 26 fields ¦ Store/ship-to location per customer — physical delivery address and store attributes
19 | Customer Store | Customer | Code | Char(7) |  | [LOB: TBD] | [TBD] | FK → Customer Master | Required
19 | Customer Store | Store | Code | Char(9) |  | [LOB: TBD] | [TBD] | Unique store code per customer | Required
19 | Customer Store | Store Name | Text | Char(60) |  | [LOB: TBD] | [TBD] |  | Required
19 | Customer Store | Doing Business As | Text | Char(40) |  | [LOB: TBD] | TBD | Trading name if different from Store Name | Optional
19 | Customer Store | Address1 | Text | Char(60) |  | [LOB: TBD] | [TBD] |  | Required
19 | Customer Store | Address2 | Text | Char(60) |  | [LOB: TBD] | [TBD] |  | Optional
19 | Customer Store | City | Text | Char(25) |  | [LOB: TBD] | [TBD] |  | Required
19 | Customer Store | STATE | Code | Char(3) |  | [LOB: TBD] | [TBD] |  | Required
19 | Customer Store | Zip Code | Text | Char(10) |  | [LOB: TBD] | [TBD] |  | Required
19 | Customer Store | Country | Code | Char(3) |  | [LOB: TBD] | [TBD] | ISO 3-char country code | Required
19 | Customer Store | Bill To Code | Code | Char(7) |  | [LOB: TBD] | TBD | FK → Customer Bill To | Optional
19 | Customer Store | Alternate Ship Thru | Flag | Char(1) |  | [LOB: TBD] | TBD | Override ship-thru flag | Amber
19 | Customer Store | Dist. Center | Code | Char(5) |  | [LOB: TBD] | TBD | FK → Customer Ship Thru / distribution centre | Optional
19 | Customer Store | Consolidator Code | Code | Char(5) |  | [LOB: TBD] | TBD | Consolidator reference code | Optional
19 | Customer Store | Old Store | Code | Char(10) |  | [LOB: TBD] | TBD | Legacy store code — clarify usage | Amber
19 | Customer Store | Location | Code | Char(6) |  | [LOB: TBD] | [TBD] | FK → Location master | Required
19 | Customer Store | Store Type | Code | Char(3) |  | [LOB: TBD] | TBD | Store classification code — list required | Amber
19 | Customer Store | Call Days For Allocation | Integer | Integer |  | [LOB: TBD] | TBD | Planning parameter — allocation scheduling | Optional
19 | Customer Store | Lead Time for Shipping | Integer | Integer |  | [LOB: TBD] | [TBD] |  | Optional
19 | Customer Store | Store Class | Code | Char(5) |  | [LOB: TBD] | TBD | Store classification tier — list required | Amber
19 | Customer Store | Store UDF 1 | Text | Char(20) |  | [LOB: TBD] | TBD | User-defined field — confirm usage with Eribé | Optional
19 | Customer Store | Store UDF 2 | Text | Char(20) |  | [LOB: TBD] | TBD | User-defined field — confirm usage with Eribé | Optional
19 | Customer Store | Active OK | Flag | Char(1) |  | [LOB: TBD] | TBD | Default Y — active/inactive status | Required
19 | Customer Store | EDI Store | Code | Char(13) |  | [LOB: TBD] | TBD | EDI store identifier | Optional
19 | Customer Store | One Time Addr Req. | Flag | Char(1) |  | [LOB: TBD] | TBD | One-time address required flag | Amber
19 | Customer Store | Address 3 | Text | Char(60) |  | [LOB: TBD] | TBD |  | Optional

## Profiling Results
Data Profiling Results
Entity / Table | Row Count | Null % (avg) | Distinct % (key fields) | Duplicate Records | Min Value | Max Value | Outliers Found | Date Range (if applicable) | Notes
Customer | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD]
Vendor | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD]
Item | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD]
G/L Entry | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD]
Customer Ledger Entry | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD]
Vendor Ledger Entry | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD]
Sales Header | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD]
Sales Line | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD]
Purchase Header | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD]
Purchase Line | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD] | [TBD]

## Quality Scorecard
Data Quality Scorecard
Score each dimension 1–5: 1=Very Poor, 2=Poor, 3=Fair, 4=Good, 5=Excellent. Overall RAG: Avg ≥4 = GREEN ¦ 2.5–3.9 = AMBER ¦ <2.5 = RED
Entity | Completeness | Consistency | Accuracy | Validity | Overall (Avg) | RAG | Data Owner | Comments
Customer | [5 empty] | GREEN | [Name]
Vendor | [5 empty] | GREEN | [Name]
Item | [5 empty] | GREEN | [Name]
G/L Entry | [5 empty] | GREEN | [Name]
Customer Ledger Entry | [5 empty] | GREEN | [Name]
Vendor Ledger Entry | [5 empty] | GREEN | [Name]
Open Sales Orders | [5 empty] | GREEN | [Name]
Open Purchase Orders | [5 empty] | GREEN | [Name]

## Issue Register
Data Quality Issue Register
# | Entity / Table | Field(s) Affected | Issue Description | Volume Estimate | Severity | Blocking? | Assigned To | Resolution / Status
1 | Customer | VAT Registration No. | ~12% of customer records have blank or invalid VAT numbers | ~300 records | High | Yes | [Owner] | Open
2 | Item | Unit Price | Negative unit prices on 45 items – likely data entry errors | 45 records | Medium | No | [Owner] | Open
3 | G/L Entry | Document No. | Duplicate document numbers across fiscal years due to year-end rollover | ~1,200 records | High | Yes | [Owner] | Open
4 | Customer | Credit Limit (LCY) | Credit limits all set to 0 – may be intentional, requires confirmation | All records | Low | No | [Owner] | Pending Confirmation
5
6
7
8
9
10
11
12
13
14

## Risk Register
Migration Risk Register
# | Risk Description | Entity / Area | Likelihood (H/M/L) | Impact (H/M/L) | Risk Score | Mitigation Strategy | Owner
1 | Poor data quality in G/L Entries may require significant cleansing effort, delaying migration timeline | G/L Entries | H | H | High | Engage Eribé finance team for data validation and sign-off | [Owner]
2 | Incomplete VAT data for customers may cause compliance issues post-migration | Customer | M | H | High | Run VAT number validation script and obtain missing numbers from Eribé | [Owner]
3 | Tribal knowledge not documented – business rules exist only in users' heads | All | H | M | High | Conduct structured stakeholder interviews; document all rules before Stage 2 | [Owner]
4 | Source system unavailable for extended profiling window | All | L | H | High | Schedule read-only access window with IT; take data snapshot | [Owner]

## Change Log
Workbook Change Log
Version | Date | Changed By | Sheet(s) Affected | Description of Change
1.0 | [Date] | [Name] | All | Initial workbook creation
04/03/2026 | Correction | All tabs | Corrected migration direction: source is LOB bespoke applications, target is BlueCherry ERP. Updated Data Dictionary title, column headers (BC Target Table → LOB Source Table, BC Target Field → LOB Source Field), field value placeholders, Source Inventory framing, and Instructions tab. | Claude